## Sheet4
Label | Priority | Stack | Status | Reported in | Closure date | Start Date | Expected delivery | Comment |  | Overview
Error while Mapping BD-Mapper ((GetReport)) | Critical | BE | Closed | 2024-09-17 |  |  | 2024-10-23 |  |  | Severity | Total Reported | Closed | Solved awaiting VF confirmation | Pending On VF | reminder
View today's data usage missing in BD page | Critical | BE | Closed | 2024-09-17 |  |  | 2024-10-23 |  |  | Critical | 16 | 15 | 1 | 0 | 0
Tibco NBA Integration | Critical | BE | Closed | 2024-08-05 | 2024-10-14 |  | 2024-10-13 |  |  | High | 55 | 41 | 2 | 1 | 12
Tibco NBA SendSMS shortcode replacement is not correct | Critical | BE & FE | Solved | 2024-11-26 |  |  | 2024-12-05
Null values logged in the Footprint | Critical | BE | Closed | 2024-09-17 |  |  | 2024-10-13 |  |  | Medium | 34 | 28 | 4 | 0 | 2
Null values logged in the TX_LOGIN | Critical | BE | Closed | 2024-09-17 |  |  | 2024-10-13 |  |  | Low | 10 | 8 | 0 | 0 | 2
Get offers UCIP does not get disabled | Critical | BE | Closed | [6 empty] | Total | 115 | 92 | 7 | 1 | 16
If a subscriber has no records in today's data usage, when pressing on the download button nothing occurs 502 error by the loadbalancer | Critical | BE | Closed | 2024-10-24 |  |  | 2024-11-06 | 5aleeh empty file
BD Report, Missing dates | Critical | FE | Closed | 2024-10-27 |  |  |  | Calendar time zone
BD Report, missing records | Critical | BE | Closed | 2024-10-27 |  |  | 2024-11-03 | BD_MAXRETRIEVALRECORDS
BD Report, Unsorted data (DESC) | Critical | BE | Closed | 2024-10-27 |  |  | 2024-11-03 | FILE_DATE_TIME_FORMAT
BD Report, Type and subType columns are swapped | Critical | BE | Closed | 2024-10-31 |  |  |  | Columns table, Type, order
No Summary usage appear | Critical | BE | Closed | 2024-10-24 |  |  | 2024-10-24
Request and session IDs are null in the lookup service's logs | Critical | BE | Closed
MSISDN Validation (Regex) | Critical | FE | Closed
Update UCIP MSISDN does not reflect in the request | Critical | FE | Closed
account history limit is affectby BD limit | High | BE & FE | Closed | 2024-10-03 | 2024-10-14 |  | 2024-10-13 | ACCOUNT_HISTORY_MAX_SEARCH_PERIOD | -
Account History ODS --> No data found Error | High | BE | Closed | 2024-10-07 |  |  | 2024-11-04
account history Search API is being called twice | High | FE | Closed | 2024-10-27
account history- data should be sorted by DateTime | High | BE | Not started | 2024-11-07 |  | 2024-12-10 | 2024-12-11 | UI tmam, files l2
account history- date and time should be displayed | High | FE | Closed | 2024-11-07 |  |  | 2024-11-20
account history - not all activity types are being displayed | High | BE | Not started | 2024-11-07 |  | 2024-12-09 | 2024-12-10 | charged service class ex
account history - subType is always empty | High | BE | Not started | 2024-11-07 |  | 2024-12-09 | 2024-12-10
account history - columns ordering should be changed | High | BE | Not started | 2024-11-05 |  | 2024-12-10 | 2024-12-09
account history - Details file always empty ((Nullpointer when sorting)) | High | BE | Closed | 2024-11-24
account history - Export for activities and activities details fail | High | FE | Closed | 2024-11-07 |  |  | 2024-11-20 | Routing URL to the gw is incorrect
Get Main Products API call should be removed | High | FE | Closed | 2024-11-17 |  |  | 2024-11-20
Offers - trying to add StopOfferMI not reflected | High | FE | Closed | 2024-09-23 |  |  | 2024-10-17 | Error with null expiry time
Offers -Null timer offer dates | High | BE | Closed | 2024-09-22 |  |  | 2024-10-13
Offers Description is incosistent | High | BE | Closed
Offers Start date should be in the future (Add/Update) | High | BE | Closed
Offers - Adding offers without expiry adds a random date instead of removing the expiry tag from the request | High | BE | Closed
Offers - a default offer start date sometimes appears in the add offer popup | High | FE | Closed
Offers - edit offer start date is allowed to be after expiry | High | FE | Closed
Offers dates is not correct | High | FE | Closed | 2024-10-02 | 2024-10-14 |  | 2024-10-13
Offers - Can't add dummy offer with ID 16 | High | BE | Closed | 2024-10-01 | 2024-10-20 |  | 2024-10-20
Offers dates edit not adjusted properly | High | FE | Closed | 2024-10-02 |  |  | 2024-10-13
Offers popup is not responsive. | High | BE & FE | Not started |  |  | 2024-12-06 | 2024-12-11
Offers & usage counter empty lists | High | BE | Not started |  |  | 2024-12-06 | 2024-12-08
products view - product quotas | High | FE | Closed | 2024-10-02 | 2024-10-17 |  | 2024-10-13 | el products btrga3 mn el BE w bytla3 No data found
products view NA valus to be represented with "NA" not "dummy" | High | FE | Closed | 2024-10-02 | 2024-10-17 |  | 2024-10-13
product view dates are not sent to FE | High | FE | Closed | 2024-10-02 | 2024-10-17 |  | 2024-10-13
can't update threshold in super flex | High | BE | Pending on VF | 2024-09-23 |  |  |  | Pending on Haneen to reproduce the case
Update SC success code However no action taken | High | BE | Closed | 2024-10-03 |  |  | 2024-10-17 | display response code
Update SC failed with some SC | High | BE | Closed | 2024-10-03 |  |  | 2024-10-17
air error in scratch card tab and in submitting voucher | High | FE | Solved | 2024-10-03 |  |  |  | infinite loop
LDAPS Integration | High | Customer | Closed | 2024-09-05
Immediate Refresh after any action is a must ((adm pending) | High | FE | Solved | 2024-09-16 |  |  |  | SMS Template and account group bits desc, Service Class
Add SMS Template returns with a NullPointerException | High | BE | Closed | 2024-11-10 |  |  | 2024-11-25
Extracting Profile Features Fails | High | BE | Closed | 2024-11-19 |  |  | 2024-11-25
Subscriber Locking should be freed automatically after 2x Token validity | High | BE | Not started | 2024-11-19 |  | 2024-12-06 | 2024-12-08
Get Voucher Server: unknown error -- cannot parse dateTime | High | BE | Closed | 2024-11-24
Dedicated account date update | High | BE | Closed | 2024-10-01 |  |  | 2024-10-20 | adjustmentAmount in the request
Dedicated account - Update: Amount is not mandatory | High | BE | Closed |  |  |  | 2024-11-03
Dedicated account - GetAll: Null dates always retrieved | High | BE | Closed |  |  |  | 2024-11-03
Dedicated account and account, No transaction limit is being applied on the subtraction | High | BE | Closed |  |  |  | 2024-11-04 | Rebate ADM_PROF_MON
Accumulators tab, reset dates are always null | High | BE | Closed | 2024-10-31 |  |  |  | Reset date to be today's date
Accumulators tab, on submit, reset date is being sent with a wrong value | High | FE | Closed | 2024-11-10
Accumulators tab, update accumulators limit adds an entry in TX_USER_MONETARY_TOTALS | High | BE | Closed |  |  |  | 2024-11-03
Prepaid VBP adjustments are not working | High | FE | Closed | 2024-09-18 | 2024-10-29 |  | 2024-10-28 | Constant values for feature ID, 6 for prepaid vbp, 2 for CB
Prepaid VBP transaction type cannot be changed | High | FE | Closed | 2024-11-05 |  |  |  | [333, 2] sent on update
FAF not changed or refreshed for new numbers | High | FE | Closed | 2024-10-03 | 2024-10-29 |  | 2024-10-20
FAF indecator lookup is incorrect | High | BE | Not started | 2024-11-25 |  | 2024-12-11 | 2024-12-12
Add Monetary Usage Counter | High | BE & FE | Not started |  |  | 2024-12-11 | 2024-12-12
serach subscriber in header or through logo doesn't call delete or add lock | High | FE | Not started | 2024-11-26
OverScratch -- Submit button is not being shown | High | FE | Closed | 2024-11-24 | 2024-12-04
Community Selected and unselected are toggled in the update | High | FE | Not started | 2024-11-20 |  | 2024-12-08 | 2024-12-09
Community Selected and unselected are toggled | High | FE | Closed | 2024-11-20
Air Buffer size | High | BE | Closed | 2024-09-10 | 2024-09-12
BD Null Null Text cannot be parsed error | High | BE | Closed | 2024-11-17 |  |  | 2024-11-20
BD range max value 30 days | High | BE | Closed
ODS Error ((OUT_CCAT_LIST)) | Medium | BE | Closed | 2024-09-10
After searching for a not available value not all pages are displayed (Mainly in admin) | Medium | FE | Solved | 2024-11-06
Send activation date in the account details | Medium | BE | Closed | 2024-10-30
Dynamic Page Not found (Privilege) | Medium | BE | Closed | 2024-09-10 | 2024-09-10
Dynamic Page deleted still appears in the ui | Medium | FE | Closed | 2024-10-03 | 2024-10-29 |  | 2024-10-28 | must refresh menus
should not apply monetary limit on accumulator | Medium | BE | Closed | 2024-10-03 | 2024-10-29 |  | 2024-10-23 | Limit = 150
BD - A reason should be taken on pressing get daily usage button | Medium | FE | Closed | 2024-11-10
show default business plan and language in advanced | Medium | FE | Closed | 2024-10-03 |  |  | 2024-11-20 | default values
Advanced: Business plan to be added instead of SC | Medium | BE & FE | Closed | 2024-10-30 |  |  | 2024-11-19
Advanced:Install Subscriber -- invalid request sent to the air server | Medium | BE & FE | Solved | 2024-11-19 |  |  |  | Nedal to send SC_ID in the install request
Admin: Batch Installation -- out of bound response from the air server | Medium | BE & FE | Solved | 2024-11-19 |  |  |  | Nedal to send SC_ID in the install request
VoucherInfo -- infinite loop on submit | Medium | FE | Not started | 2024-11-24 |  | 2024-12-08 | 2024-12-09
Service Class - refresh after action | Medium | FE | Solved | 2024-11-18
Get Voucher Details - Update State - Get Voucher History --> Static operator ID = Main | Medium | BE | Closed | 2024-11-18 |  |  | 2024-11-20
NBA gift description modifcations | Medium | FE | Not started | 2024-11-20 |  | 2024-12-09 | 2024-12-10
no unlink in Transaction admin | Medium | FE | Closed | 2024-09-17
Transaction type & code not mandatory in Accumulators tab | Medium | FE | Closed | 2024-09-17
Transaction code could be deleted even if it has a link | Medium | BE | Closed | 2024-11-06
Send SMS in Service Class | Medium | BE | Closed
Product ID missing | Medium | FE | Closed | 2024-10-03 |  |  | 2024-10-13
Doesn't validate different values for fields in transaction admin | Medium | FE | Closed | 2024-09-24 |  |  | 2024-10-24 |  | -
Add Transaction code Database Error (Sequence) | Medium | BE | Closed |  |  |  |  | DataDatabase Error, PreparedStatementCallback; SQL [INSERT INTO ADM_TX_CODES(ID,NAME,VALUE,DESCRIPTION) values ( S_ADM_TX_CODES.nextval, ? , ? , ? )]; ORA-00001: unique constraintbase Error, PreparedStatementCallback; SQL [INSERT INTO ADM_TX_CODES(ID,NAME,VALUE,DESCRIPTION) values ( S_ADM_TX_CODES.nextval, ? , ? , ? )]; ORA-00001: unique constraint | -
Rating Groups | Medium | BE | Closed | 2024-07-31
Send SMS Flag | Medium | BE | Closed | 2024-07-24 | 2024-09-22
Lookup refresh | Medium | BE | Closed | 2024-09-16 | 2024-09-22
Failed logins throw exception which will lead to false alarms | Medium | BE | Closed |  | 2024-09-22
Update schema in BD service | Medium | BE | Closed |  | 2024-09-16
MSISDN Locking while token expiry | Medium | BE & FE | Closed | 2024-09-16 |  |  | 2024-10-28
MSISDN Force unlock (duplicate sessions) | Medium | BE & FE | Closed |  |  |  | 2024-10-28
2nd MSISDN Search the dial still locked | Medium | FE | Closed
Type error in navigating to call reason tab | Medium | FE | Closed
Dedicated Account Decimal Adjustment | Medium | FE | Closed
subtract in account administration does not accept decimal | Medium | FE | Closed
Dedicated Account refresh after adjustment | Medium | FE | Closed
Update Monetary Counter UCIP need to use usageCounterMonetaryValueNew instead of usageCounterValueNew | Low | FE | Not started | 2024-09-11 |  | 2024-12-09 | 2024-12-10
No offers returns unknown errors | Low | BE | Closed | 2024-10-29
Deprecate flex share page in Customer care | Low | BE | Closed | 2024-09-05 |  |  |  | etshalet mn el adm
need to automatically move to next cell in voucher | Low | FE | Closed | 2024-10-03 | 2024-10-21
no unbar text | Low | FE | Closed | 2024-10-03
Business plan creation | Low | BE | Closed
Can't download batch disconnection template | Low | FE | Closed
Complaint view page header | Low | FE | Closed
Offer description not shown in offers tab | Low | FE | Closed
No reason should be taken when exporting Balance Dispute report | Low | FE | Not started |  |  | 2024-12-09 | 2024-12-10

## UI-UX
Function | UI Change | Priority | Comment | Expected Delivery
NBA Auto Float | While pointing grid floating Has To Stopped |  | in popup and sidebar
NBA Floating Time | Increase Floating Time |  | in popup and sidebar
NBA Arrow Button | Use Icon Instead |  | in sidebar
NBA Script | Margine Top Center |  | centre or right
NBA Buttons | Action Button
Solved | Icon should not be pixelated
Product View | Bars Alignments Left
Product View | Bars Colors 0% to 80 % Green 80% to 99 % Orange 99% To 100% Red
Product View | No sorting in "Name" column
Product View | Typo in "Renewal Date"
Product View | Remaining Quota / Total Quota values are swapped beside graphical bar when quotas expanded
Offers Popup | Enhance performance in loading offers |  |  | 2024-12-11
Offers Tab | Static Colors For Fixed Offers
Offers Tab | Set History For Delete/Add Offers In Notepad
Offers Tab | Show Offers IDs While Adding From Drop Down Menu
Balances | Limit Characters Fields
Balances | Dedicated Description
Balances | Set Reason For Add/Subtract Balances
Balance Dispute | Daily usage Replace icon with text as account history
Balance Dispute | BD Report Replace icon with text as account history
Note Pad | Allow Selection Tick Box Instead Of Delete All Notes Button
Character Fields | Limiting Character Fields
Any view with a table (ex. Offers, Products View) | Table header should not disappear when no data found after filtering or searching (this UX suggests to the user that the page failed loading), instead show an empty table |  | don in admin menu
Any view with a table (ex. Offers, Products View) | Sorting does not work with some columns (ex: "Name" in Product View, "User Name" in Locking Administration)
Header Bar | Padding between version number and datetime (on the left) should be equal to the padding on the right
Batch Install / Disconnect | Validation text (total, success, failed) styling gets messed up when sidebar is opened
Call Reason | Reasons typo in call activity page
Account Administration | Add/Subtract amount should remain visible when active even when hovering outside of it
System Settings | Procedure service --> flex share boxes
System Settings | User management --> LDAP flag always checked [true or false]
External Node [AIR] | In the edit or add box authorization is repeated twice
External Node [AIR] | Host field is mandatory However not specified in UI
External Node [AIR] | In add AIR save button is not enabled until we change the status to down
Adminstrators/Family and Freinds plans | in Edit FaF Plan, Plan ID should be dimmed
Customer Care/Super Flex view & Usage Counters | in MI Threshold tab, when the right sidebar opens the page content doesn't adjust its layout accordingly.

## DSS Reports
Pages | UI | Integration | Simulator | DAO | Services | Testing | Duration
BTIVR | Done | 1 day | 2 days | 3 hrs | 1 day | 1 day |  | 2024-12-08
Contract Bill | Done |  | 2 days |  |  | 1 day
Contract Balance | Done | 1 day | 2 days |  | 1 day | 1 day
Contract Balance Transefer | Done |  | 2 days |  |  | 1 day
Complaint View | Done | 1 day | 2 days |  | 1 day | 1 day |  | 2024-12-08
ETOPUP | Done |  | 2 days |  |  | 1 day
Outgoing View | Done | 1 day | 2 days |  | 1 day | 1 day
Traffic Behaviour | Done |  | 2 days |  |  | 1 day
USSD Report | Done | 1 day | 2 days |  | 1 day | 1 day |  | 2024-12-15
Visited URLs | Done |  | 2 days |  |  | 1 day |  | 2024-12-15
Vodafone One | Done | 1 day | 2 days |  | 1 day | 1 day
Vodafone One Redeem | Done |  | 2 days |  |  | 1 day